## Details
RallyNSW
Event Organisers' Flowchart
Primary Event Details:
Yr & Event Name | 2021 Sample Event
Start date | 2021-07-01
Location (town)
Series details
Organisers' info on RallyNSW website: |  | http://www.rallynsw.com.au/info/organisers
Key Event Personnel |  |  | Key RallyNSW Personnel
Clerk of Course |  |  | Panel Event Liaison
Name |  |  | Name | TBA |  | Entered | Due | Days until Due
Initials (2) | CO |  | Initials (2) | TB | Clerk of Course | 0 | 2021-03-03 | 0
Mobile Number |  |  | Mobile Number |  | Event Secretary | 0 | 2021-03-03 | 0
Email Address |  |  | Email Address | EventAssist@rallynsw.com.au | Event Media Officer | 0 | 2021-03-03 | 0
[5 empty] | Event Results Officer | 0 | 2021-03-03 | 0
Event Secretary |  |  | Panel Media Liaison |  | Event Checker | 0 | 2021-03-03 | 0
Name |  |  | Name | John McCredie | Media Assistant #1 | 0 | 2021-06-03 | 92
Initials (2) | ES |  | Initials (2) | JM | Media Assistant #2 | 0 | 2021-06-03 | 92
Mobile Number |  |  | Mobile Number | 0413 042 763
Email Address |  |  | Email Address | MediaAssist@rallynsw.com.au | Panel Event Liaison | 1 | 2021-03-03
[5 empty] | Panel Media Liaison | 1 | 2021-03-03
Event Media Officer |  |  | Panel Results Liaison |  | Panel Results Liaison | 1 | 2021-03-03
Name |  |  | Name | Bethany Cullen | Panel on-event rep | 0 | 2021-03-03 | 0
Initials (2) | EM |  | Initials (2) | BC | Panel Google Drive coordinator | 1 | 2021-03-03
Mobile Number |  |  | Mobile Number | TBA | Panel Social Media Coordinator | 1 | 2021-03-03
Email Address |  |  | Email Address | ResultsAssist@rallynsw.com.au | Panel Partnerships coordinator | 1 | 2021-03-03
[5 empty] | Panel Secretarial coordinator | 1 | 2021-03-03
Event Results Officer |  |  | Panel On-Event Representative |  | 15 | 7 |  | 0
Name |  |  | Name
Initials (2) | ER |  | Initials (2)
Mobile Number |  |  | Mobile Number
Email Address |  |  | Email Address
Event Checker |  |  | Panel Google Drive Coordinator
Name |  |  | Initials (2) | GC
Initials (2) | EC
Mobile Number |  |  | Panel Competitor and Social Media Coordinator
Email Address
|  |  | Initials (2) | PC
Media Assistant #1
Name |  |  | Panel Partnerships Coordinator
Mobile Number |  |  | Initials (2) | PP
Email Address
Panel Secretarial Coordinator
Media Assistant #2 |  |  | Initials (2) | PS
Name
Mobile Number
Email Address
Formulas:
Days until Due = IF([Due]="","", [Due]-TODAY())

## Progress
2021 Sample Event
Progress recording
This page is intended to give a quick overview of how planning is proceeding for your event. Keeping the flowchart up to date will help you by keeping RallyNSW updated on your progress, enabling them to offer assistance when needed.
Module | Progress | Days until due | Status
Personnel Details | 46.67% | 0 | OVERDUE
Module 1 - Pre-Planning | 0% | -245 | OVERDUE
Module 2 - Planning | 0% | -160 | OVERDUE
Module 3 - Finalising Approvals & Early Preparations | 0% | 36 | OK
Module 4 - Preparation & Setup | 0% | 78 | OK
Module 5 - Day of Competition and Post-Event | 0% | 120 | OK

## 1 Pre-Planning
2021 Sample Event
Module 1 - Pre-Planning
Previous Year
The pre-planning phase is about making sure the pieces are all in place to set the event on a course to success. The steps here will enable RallyNSW to begin promoting your event, ensuring that everyone is working together to make it a raging success!
Item No. & Form | Task and person responsible |  | Date Due | Done By | Date Completed | Comments
1 year prior to event | [6 empty] | Complete | Due | Days until Next Due
1.01 | Introductory phone call to Clerk of Course from RallyNSW Event Liaison | TB | 2020-07-01 |  |  |  | 0 | 2020-07-01 | -245
1.02 | Event folder created in RallyNSW Google Drive | GC | 2020-07-01 |  |  |  | 0 | 2020-07-01 | -245
1.03 | Event google Drive Folder shared to Clerk of Course | TB | 2020-07-01 |  |  |  | 0 | 2020-07-01 | -245
1.04 | Event Logo prepared | CO | 2020-07-01 |  |  |  | 0 | 2020-07-01 | -245
1.05 | Event Logo added to RallyNSW Google Drive Folder | CO | 2020-07-01 |  |  |  | 0 | 2020-07-01 | -245
1.06 | Facebook Event Created | PC | 2020-07-01 |  |  |  | 0 | 2020-07-01 | -245
1.07 | Facebook event co-hosted by organising club | CO | 2020-07-01 |  |  |  | 0 | 2020-07-01 | -245
Total Items | 7 |  |  |  |  | Totals done and days until next due: | 0 |  | -245
Formulas:
Due = IF([Complete]=0,[Date Due],"")
Days until Next Due = IF([Due]="","", [Due]-TODAY())
Days until Next Due = [Date Due]-TODAY()

## 2 Planning
2021 Sample Event
Module 2 - Planning
Between 3 and 10 months prior to event
The planning phase is about ensuring that your event's foundation is solid and that plans are in place to deliver a smooth approvals process.
Item No. & Form |  | Task and person responsible |  | Date Due | Done By | Date Completed | Comments | Complete | Due | Days until Next Due
Before 40 weeks prior to event
2.01 |  | Nominate all key Event Officials - Event Secretary, Road Director, Chief Scrutineer, Event Media Liaison, Event Results officer) | CO | 2020-09-24 |  |  |  | 0 | 2020-09-24 | -160
2.02 | Yes | Apply to RallyNSW for an Event Checker | CO | 2020-09-24 |  |  |  | 0 | 2020-09-24 | -160
2.03 |  | Enter Event Media Coordinator's details in this form (on Summary tab) | CO | 2020-09-24 |  |  |  | 0 | 2020-09-24 | -160
2.04 |  | Secure Event Sponsorship | CO | 2020-09-24 |  |  |  | 0 | 2020-09-24 | -160
2.05 | Yes | Create a marketing and promotions plan | CO | 2020-09-24 |  |  |  | 0 | 2020-09-24 | -160
Before 32 weeks prior to event
2.06 |  | Obtain maps of the proposed area | CO | 2020-11-19 |  |  |  | 0 | 2020-11-19 | -104
2.07 |  | Contact Forestry NSW to discuss availability, likely road condition, residents (especially those suspected of having an issue with the event) and management plans | CO | 2020-11-19 |  |  |  | 0 | 2020-11-19 | -104
2.08 |  | Contact the local council to discuss facility and road use, possible event clashes and resident contact details | CO | 2020-11-19 |  |  |  | 0 | 2020-11-19 | -104
2.09 |  | Confirm intended Rally HQ has adequate data service for results. | CO
2.1 | Yes | Create a basic event format plan | CO | 2020-11-19 |  |  |  | 0 | 2020-11-19 | -104
2.11 |  | Estimate entry numbers to allow budgeting | CO | 2020-11-19 |  |  |  | 0 | 2020-11-19 | -104
2.12 |  | Create an event budget | CO | 2020-11-19 |  |  |  | 0 | 2020-11-19 | -104
Before 24 weeks prior to event
2.13 |  | Survey the roads you've chosen, ensuring that no competitive sections extend into National Parks | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
2.14 |  | Contact NPWS (where appropriate) to confirm whether liaison stages are permitted to traverse roads in the park | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
2.15 |  | Check all planned control points for mobile phone and radio reception | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
2.16 |  | Confirm the planned service park(s) have a suitable all-weather surface and are large enough to hold the required number of teams | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
2.17 |  | Plan spectator areas that are suitable and have adequate parking and acceptable access | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
2.18 |  | Note the sunset time for the day of competition (including daylight savings) | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
2.19 |  | Plan service vehicle routes that avoid unsealed roads where possible | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
2.2 |  | Plan spectator routes that avoid unsealed roads where possible | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
2.21 | Yes | Present initial event plans to the Event Checker | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
2.22 | Yes | Discuss your Media and Promotions plans with the Panel Media Liaison | CO | 2021-01-14 |  |  |  | 0 | 2021-01-14 | -48
Before 18 weeks prior to event
2.23 |  | Mark control locations (using something that won't be graded over or damage trees etc) | CO | 2021-02-25 |  |  |  | 0 | 2021-02-25 | -6
2.24 | Yes | Visit Forestry NSW with detailed overview maps and control diagrams and a draft itinerary | CO | 2021-02-25 |  |  |  | 0 | 2021-02-25 | -6
2.25 | Yes | Confirm forestry plans around the time of the event and seek verbal approval from Forestry | CO | 2021-02-25 |  |  |  | 0 | 2021-02-25 | -6
2.26 |  | Visit local Council offices with same plans | CO | 2021-02-25 |  |  |  | 0 | 2021-02-25 | -6
2.27 |  | Confirm residents details and community plans around the time of the event and seek verbal approval from Councils | CO | 2021-02-25 |  |  |  | 0 | 2021-02-25 | -6
2.28 |  | Book live results system | TB | 2021-02-25 |  |  |  | 0 | 2021-02-25 | -6
Total Items |  | 28 | [5 empty] | 0 |  | -160
Formulas:
Due = IF([Complete]=0,[Date Due],"")
Days until Next Due = IF([Due]="","", [Due]-TODAY())

## 3 Approvals
2021 Sample Event
Module 3 - Finalising Approvals & Early Preparations
Between 2 and 3 months prior to event
The approvals and early preparation phase is about ensuring that all the pieces are in place to have the event run safely, efficiently and with the permission of the related authorities.
Item No. & Form |  | Task and person responsible |  | Date Due | Done By | Date Completed | Comments | Complete | Due | Days until Next Due
Before 12 weeks prior to event
3.01 |  | Create formal approval documents for Police, Forestry and Councils that contain a traffic management plan (samples on RallyNSW website), all media day and event maps (with road closures including sign locations plus competitive, liaison, service, spectator and HQ details), and a short description of the event in layman's terms | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.02 | Yes | Apply to Police | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.03 | Yes | Apply to Forestry NSW | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.04 | Yes | Apply to Councils | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.05 | Yes | Prepare draft Supp Regs (template available on RallyNSW Website) | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.06 | Yes | Prepare draft Road Book including forms, alternate routes and itinerary (template available on RallyNSW Website) | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.07 |  | Provide all documents to Event Checker | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.08 |  | Save draft event documents in RallyNSW Google Drive folder | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.09 | Yes | Provide Rally NSW with details of assets and consumables required (clocks, car numbers, door panels, promotional banners and start arch) by saving form(s) in RallyNSW Google Drive folder | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.1 |  | Save all event partner and sponsor logos in RallyNSW Google Drive folder | CO | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
3.11 |  | Create event poster and arrange printing & shipping to Event Media Liaison | TB | 2021-04-08 |  |  |  | 0 | 2021-04-08 | 36
Before 10 weeks prior to event
3.12 | Yes | Provide RallyNSW with Pre-Event promotional material by saving in RallyNSW Google Drive folder | CO | 2021-04-22 |  |  |  | 0 | 2021-04-22 | 50
3.13 |  | Distribute pre-event promotional material to RallyNSW Database | PC | 2021-04-22 |  |  |  | 0 | 2021-04-22 | 50
3.14 |  | Undertake full physical course check (including spectator and service crew routes) | EC | 2021-04-22 |  |  |  | 0 | 2021-04-22 | 50
Before 9 weeks prior to event
3.15 | Yes | Prepare a Motorsport Australia Permit Application Form | CO | 2021-04-29 |  |  |  | 0 | 2021-04-29 | 57
3.16 | Yes | Prepare a Motorsport Australia Safety First checklist | CO | 2021-04-29 |  |  |  | 0 | 2021-04-29 | 57
3.17 | Yes | Prepare a Motorsport Australia Medical Response Plan B Form | CO | 2021-04-29 |  |  |  | 0 | 2021-04-29 | 57
3.18 |  | Submit above forms and Supp Regs, entry form and Event Checker's report to permits@motorsport.org.au CC copy of Supp Regs to rallypanel@rallynsw.com.au to expidite approvals. (NOTE: this has a solid 8 week deadline) | CO | 2021-04-29 |  |  |  | 0 | 2021-04-29 | 57
3.19 |  | Save all documents to the RallyNSW Google Drive Folder | CO | 2021-04-29 |  |  |  | 0 | 2021-04-29 | 57
Total Items |  | 19 | [5 empty] | 0 |  | 36
Formulas:
Due = IF([Complete]=0,[Date Due],"")
Days until Next Due = IF([Due]="","", [Due]-TODAY())

## 4 Prep & Setup
2021 Sample Event
Module 4 - Preparation & Setup
2 months to 1 day prior to event
The preparation and setup phase is about ensuring that the event is prepped and ready to run smoothly on the day, without causing any more disturbance than is necessary to the public.
Item No. & Form |  | Task and person responsible |  | Date Due | Done By | Date Completed | Comments | Complete | Due | Days until Next Due
Before 6 weeks prior to event
4.01 | Yes | Set up Event Management Plan | CO | 2021-05-20 |  |  |  | 0 | 2021-05-20 | 78
4.02 | Yes | Set up Personnel Management Plan | CO | 2021-05-20 |  |  |  | 0 | 2021-05-20 | 78
4.03 | Yes | Lock in officials for major roles - stage commanders, service park managers and refuel area managers | CO | 2021-05-20 |  |  |  | 0 | 2021-05-20 | 78
4.04 |  | Publish Supp Regs (only once approved by Motorsport Australia) | CO | 2021-05-20 |  |  |  | 0 | 2021-05-20 | 78
4.05 |  | Save Supp Regs and maps in RallyNSW Google Drive folder | CO | 2021-05-20 |  |  |  | 0 | 2021-05-20 | 78
4.06 |  | Distribute Supp Regs to registered competitors | PC | 2021-05-20 |  |  |  | 0 | 2021-05-20 | 78
4.07 | Yes | Ensure a robust process is in place for managing entries and entry fees | CO | 2021-05-20 |  |  |  | 0 | 2021-05-20 | 78
4.08 |  | Arrange printing and shipping of event-specific posters | JM | 2021-05-20 |  |  |  | 0 | 2021-05-20 | 78
Before 4 weeks prior to event
4.09 | Yes | Erect road closure signs (at least 900X600mm). Must show closure times, road names, and contact details) | CO | 2021-06-03 |  |  |  | 0 | 2021-06-03 | 92
4.1 | Yes | Visit all residents on the route (leaving a letter for those not home - template on the RallyNSW website) | CO | 2021-06-03 |  |  |  | 0 | 2021-06-03 | 92
4.11 |  | Distribute event posters to shops and businesses in the local area, sticking them on shop windows yourself. | EM | 2021-06-03 |  |  |  | 0 | 2021-06-03 | 92
4.12 |  | Recruit event personnel (road closures and control officials) | CO | 2021-06-03 |  |  |  | 0 | 2021-06-03 | 92
4.13 |  | Save electronic map (KMZ or GPX) in RallyNSW Google Drive folder | EM | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.14 | Yes | Nominate 2 volunteer assistants for RallyNSW Media Team (one needs a reliable 4WD and both need good local knowledge) | CO | 2021-06-03 |  |  |  | 0 | 2021-06-03 | 92
4.15 | Yes | Arrange shipping of RallyNSW Assets (clocks, banners, arch, series stickers, etc) | TB | 2021-06-03 |  |  |  | 0 | 2021-06-03 | 92
Before 2 weeks prior to event
4.16 |  | Ensure all residents have been contacted | CO | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.17 | Yes | Advise local hospital of the event - template letter available on RallyNSW website | CO | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.18 | Yes | Advise local Ambulance service of the event, supplying itinerary and maps - template letter available on RallyNSW website | CO | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.19 |  | Complete final course check - ensure instructions are accurate, removing any large rocks and branches from the road | CO | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.2 |  | Save final road book to RallyNSW Google Drive Folder | CO | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.21 |  | Contact all road closure and control officials, providing safety plan, role details and list of what to bring - templates on RallyNSW Website | CO | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.22 |  | Ensure you've received written approval from all authorities | CO | 2021-06-17
4.23 |  | Forward each approval document to all other authorities | CO | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.24 |  | Save approval docs in RallyNSW Google Drive folder | CO | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.25 | Yes | Book accommodation for RallyNSW Media Team (up to 4 people twin share for the nights before and after the event) | EM | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.26 |  | Contact Event Results Co-ordinator to ensure they are confident using the results system | BC | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.27 |  | Documentation for registered competitors to be emailed to event secretary | PC | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
4.28 |  | Share Event Documentation folder to Event Secretary | TB | 2021-06-17 |  |  |  | 0 | 2021-06-17 | 106
Before 1 week prior to event
4.29 | Yes | Assemble control packs - Contents list on RallyNSW Website | CO | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.3 | Yes | Order RallyNSW Bags and lanyards by saving form in RallyNSW Google Drive Folder | CO | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.31 |  | Arrange for shipping of RallyNSW bags and Lanyards | TB | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.32 |  | Save Fast Lane Documentation certificate for registered competitors to Event Google Drive folder | PC | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.33 | Yes | Publish Road Closure Notice in local newspapers | CO | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.34 | Yes | Publish seeded list of entries | CO | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.35 |  | Save entry list in RallyNSW Google Drive Folder | CO | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.36 |  | Send Entry list (including classes) and itinerary to results provider | BC | 2021-06-24
4.37 |  | Print and bind all documents | CO | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.38 | Yes | Prepare competitor packs | CO | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.39 | Yes | Prepare Media Personnel pack - 3 event radios plus (as required) key to locked gates, vehicle stickers and passes | CO | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.4 |  | Camera Schedule to be saved into RallyNSW Google Drive Folder | JM | 2021-06-28 |  |  |  | 0 | 2021-06-28 | 117
4.41 |  | Notify Clerk of Course that camera schedule is available | JM | 2021-06-28 |  |  |  | 0 | 2021-06-28 | 117
4.42 |  | Ensure the Even Media Officer has a device with the event's email account installed and operational | EM | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.43 |  | Ensure the Event Media Officer has access to the event's Facebook page | EM | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
4.44 |  | Establish email and social media contact with RallyNSW Partnerships coordinator, all event partners and sponsors, as well as local council etc | EM | 2021-06-24 |  |  |  | 0 | 2021-06-24 | 113
1 day prior to event
4.45 |  | Set up Rally HQ | CO | 2021-06-30 |  |  |  | 0 | 2021-06-30 | 119
4.46 |  | Set up Stages | CO | 2021-06-30 |  |  |  | 0 | 2021-06-30 | 119
4.47 |  | Set up service Park | CO | 2021-06-30 |  |  |  | 0 | 2021-06-30 | 119
4.48 |  | Conduct Media/Test Day (If applicable) | CO | 2021-06-30 |  |  |  | 0 | 2021-06-30 | 119
Total Items |  | 48 | [5 empty] | 0 |  | 78
Formulas:
Due = IF([Complete]=0,[Date Due],"")
Days until Next Due = IF([Due]="","", [Due]-TODAY())

## 5 Event & Post
Module 5 - Day of Competition and Post-Event
Day of to 1 week after the event
The day of competition is when everything comes together and the deliverables are provided to both the event's customers (competitors) and sponsors. The post event phase is about ensuring that all tasks have been completed, all stakeholders are aware of the event's delivered outcomes and all who have given their time and resources have been thanked.
Item No. & Form |  | Task and person responsible |  | Date Due | Done By | Date Completed | Comments | Complete | Due | Days until Next Due
Day of Competition
4.01 |  | Tag all event sponsors, partners, councils etc in each video that is shared on social media by the RallyNSW Media team | EM | 2021-07-01 |  |  |  | 0 | 2021-07-01 | 120
4.02 |  | Email a link to each video to the RallyNSW Partnerships coordinator, each event sponsor, partner, council etc | EM | 2021-07-01 |  |  |  | 0 | 2021-07-01 | 120
1 day after Competition
4.03 |  | Remove all trace of event from the forest (if not done already) | CO | 2021-07-02 |  |  |  | 0 | 2021-07-02 | 121
4.04 |  | Tag all event sponsors, partners, councils etc in each video that is shared on social media by the RallyNSW Media team post event | EM | 2021-07-02 |  |  |  | 0 | 2021-07-02 | 121
4.05 |  | Email a link to each video to the RallyNSW Partnerships coordinator, each event sponsor, partner, council etc | EM | 2021-07-02 |  |  |  | 0 | 2021-07-02 | 121
4.06 |  | Save results to RallyNSW Google Drive folder in Excel format (if not using online results system) | ER | 2021-07-02 |  |  |  | 0 | 2021-07-02 | 121
4.07 |  | Email and SMS results to registered competitors | PC | 2021-07-02 |  |  |  | 0 | 2021-07-02 | 121
4.08 |  | Upload results to RallyNSW Website and publish on Facebook | PC | 2021-07-02 |  |  |  | 0 | 2021-07-02 | 121
2 days after Competition
4.09 |  | Calculate point scores following event | BC | 2021-07-02 |  |  |  | 0 | 2021-07-02 | 121
4.1 |  | Save point scores to RallyNSW Google Drive folder | BC | 2021-07-03 |  |  |  | 0 | 2021-07-03 | 122
4.11 |  | Email point scores to registered competitors | PC | 2021-07-03 |  |  |  | 0 | 2021-07-03 | 122
4.12 |  | Upload point scores to RallyNSW Website and publish on Facebook | PC | 2021-07-03 |  |  |  | 0 | 2021-07-03 | 122
Before 1 week after Competition
4.13 | Yes | Collate media deliverables since end of previous event and produce post-event media report | PP | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.14 |  | Save post event media report to RallyNSW Google Drive folder | TB | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.15 |  | Notify Clerk of Course of media report availability | TB | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.16 |  | Email post-event media report to all series partners and sponsors | PP | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.17 |  | Email post-event media report to all event partners and sponsors as well as councils etc | EM | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.18 | Yes | Prepare and distribute letters of thanks to all authorities and residents | CO | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.19 | Yes | Submit Clerk of Course Post Event form | CO | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.2 | Yes | Submit post-event fee form | CO | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.21 | Yes | Submit post-event Checker's Report to permits@motorsport.org.au | EC | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.22 |  | Submit PDF of final results from ChrisSport to permits@motorsport.org.au | ER | 2021-07-08
4.23 |  | Save post event Checker's Report to RallyNSW Google Drive folder | CO | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
4.24 |  | Destroy any credit card details collected | CO | 2021-07-08 |  |  |  | 0 | 2021-07-08 | 127
Total Items |  | 24 | [5 empty] | 0 |  | 120
Formulas:
Due = IF([Complete]=0,[Date Due],"")
Days until Next Due = IF([Due]="","", [Due]-TODAY())